# The High Authority Benefits Governance Guide

Identification, Realisation and Review under Controlled Accountability

Author

James J. Bailey

Project Management and Business Case Advisory

Connect on LinkedIn

https://www.linkedin.com/in/jamesbailey-uk/

# Part 0. How Benefits Governance Fits Beneath the Business Case and Delivery Controls

Projects are approved because they promise value.

The Business Case sets out the strategic case for change, the economic justification and the expected benefits. Approval is given on the basis that those benefits will be realised.

However, approval does not deliver value. Delivery must be governed, and benefits must be actively managed.

Benefits governance therefore sits across the full lifecycle of a project:

- The Business Case defines why the investment is justified and what value is expected.

- The Benefits Management Strategy defines how those benefits will be structured, owned, measured and tracked.

- The PID and Stage Plans define how the project will be delivered under controlled tolerances.

- The Benefits Realisation Plan and Review process confirm whether value has actually been achieved.

In practice, many organisations stop at approval. Benefits are described, sometimes quantified, and then largely forgotten once delivery begins. Measurement is delayed. Ownership is unclear. Reporting becomes inconsistent.

High-authority governance does not treat benefits as an appendix to the Business Case. It treats them as an accountability mechanism.

What This Document Is Not

This document does not attempt to restate project management theory.
It does not duplicate the Business Case.
It does not replace the PID or Stage Plans.

It provides a structured mechanism for ensuring that approved value is realised, measured and governed.

Governance Reality

In many organisations:

- Benefits are approved at investment stage

- Delivery focuses on outputs

- Operational adoption is assumed

- Measurement is delayed or diluted

This guide is designed to prevent that failure mode.

Three principles underpin effective benefits governance:

1. Benefits must remain linked to strategic objectives.

If a benefit cannot be traced back to a strategic aim, it becomes operational noise rather than investment justification.

2. Benefits must have named ownership.

Delivery teams build outputs. Operational leaders realise benefits. Accountability cannot be implied.

3. Benefits must be measured against baselines.

Without defined baseline values and target measures, improvement cannot be demonstrated.

In structured governance environments, the Senior Responsible Owner remains accountable for ensuring that benefits are realised, even after project closure. Realisation may continue well beyond the final stage of delivery.

This guide sets out a practical, controlled approach to:

- Structuring a Benefits Management Strategy

- Defining measurable and owned benefits

- Aligning benefits to delivery milestones

- Monitoring realisation

- Formally reviewing and signing off value

The purpose is not to create additional paperwork. It is to ensure that approved investment translates into demonstrable outcomes.

- The Business Case justifies the decision

- The PID governs delivery.

- Benefits governance confirms value.

# Part 1. What Reviewers Actually Look For in Benefits Governance

How This Section Should Be Used

Use this section as a diagnostic tool before submission.
If a benefit cannot withstand these scrutiny tests, it should not proceed unchallenged.

Review panels are less interested in narrative and more concerned with defensible evidence.

In formal governance environments, benefits documentation is not read for narrative quality. It is examined for assurance.

Reviewers are looking for evidence that value is defined, controlled and realistically achievable.

The following areas are consistently tested.

## 1. Clear Link to Strategic Objectives

Reviewers will look for explicit alignment between each benefit and a stated strategic objective.

This is not a general statement that the project supports strategy. It is a demonstrable line of sight:

- Strategic objective

- Required business change

- Expected outcome

- Measurable benefit

If that chain cannot be traced, the benefit is weak.

Common Weakness

Benefits described in isolation without explicit linkage to approved strategic objectives.

Prompt for Review

Can this benefit be traced directly to a documented strategic objective or policy commitment?

## 2. Defined and Owned Benefits

Each benefit must have:

- A named benefit owner

- Clear accountability for realisation

- Authority within the operational environment

Delivery teams create outputs. They do not automatically realise benefits. Reviewers will test whether ownership sits with the correct operational leader.

If ownership is unclear, benefits are unlikely to materialise.

Common Weakness

Benefits assigned to the project team rather than to operational leaders responsible for ongoing performance.

Prompt for Review

Is the named benefit owner senior enough to influence the operational change required?

## 3. Baselines and Target Measures

A benefit without a baseline is an aspiration.

Reviewers expect to see:

- Current performance level

- Target performance level

- Measurement unit

- Measurement method

- Frequency of measurement

Claims such as “improved efficiency” or “enhanced performance” are not sufficient. Benefits must be measurable or assessable in a structured way.

Common Weakness

Targets defined without an evidenced baseline.

Prompt for Review

What documented data source proves the starting position?

## 4. Realistic Assumptions

Benefits are often built on assumptions regarding:

- Adoption rates

- Behavioural change

- Resource availability

- External dependencies

Reviewers will test whether these assumptions are stated and whether they are credible. Unrealistic assumptions weaken the entire justification.

Common Weakness

Adoption rates, behavioural changes or capacity improvements assumed without supporting evidence.

Prompt for Review

What evidence supports the assumptions underpinning this benefit forecast?

## 5. Alignment to Delivery Milestones

Benefits should be linked to:

- Go live events

- Stage completions

- Operational transitions

Reviewers will examine whether the benefits realisation schedule aligns with the delivery plan. If milestones and benefits are disconnected, governance control is weak.

Common Weakness

Benefits forecast to materialise before operational capability or system stability is realistically achievable.

Prompt for Review

Does the timing of this benefit logically follow the relevant delivery milestone?

## 6. Resource and Capability to Realise Benefits

Realisation often requires:

- Training

- Process redesign

- Behavioural change

- Ongoing monitoring

Reviewers will check whether:

- Resources are allocated

- Skills gaps are identified

- Operational capacity exists to implement change

Without capability, benefits remain theoretical.

Common Weakness

Benefits dependent on training or process change without funded resource or confirmed capacity.

Prompt for Review

What operational resource has been formally allocated to enable this benefit?

## 7. Governance and Reporting Framework

Reviewers look for:

- Defined reporting cycle

- Escalation routes for underperformance

- Integration with programme or board reporting

- Clear decision points for remedial action

Benefits governance must sit within existing governance structures. It should not operate in isolation.

Common Weakness

Benefits reporting described informally without defined frequency, format or escalation route.

Prompt for Review

If this benefit underperforms, who is formally notified and through what mechanism?

## 8. Risk and Dependency Management

Benefits carry risk.

Reviewers expect to see:

- Risks to benefit realisation identified

- Dependencies mapped

- Mitigation strategies defined

If risk is only assessed at project delivery level and not at benefit level, governance is incomplete.

Common Weakness

Project risks documented, but no explicit analysis of risks to benefit realisation.

Prompt for Review

What could prevent this benefit from materialising even if the project delivers successfully?

## 9. Post Closure Accountability

Benefits frequently continue beyond project closure.

Reviewers will test:

- Who remains accountable after closure

- How measurement continues

- When formal sign off will occur

If accountability ends at delivery completion, value is not controlled.

Common Weakness

Measurement responsibility ends at project closure.

Prompt for Review

Who retains accountability for this benefit six months after project closure?

## 10. Evidence of Structured Thinking

Finally, reviewers look for discipline.

Benefits should be:

- Prioritised

- Structured

- Categorised

- Consistent in definition

- Free from duplication

A small, well defined set of benefits is stronger than an extensive list of loosely defined aspirations.

Effective benefits governance is not about optimism. It is about controlled accountability.

If benefits are:

- Strategically aligned

- Owned

- Measured

- Resourced

- Reported

- Reviewed

Then investment justification can withstand scrutiny.

Common Weakness

Long lists of loosely defined aspirations presented as measurable benefits.

Prompt for Review

Have benefits been prioritised and rationalised to focus on material outcomes?

# Part 2. The Benefits Management Strategy Template

## How to Use the Benefits Management Strategy Template

This template is designed to be completed progressively as the project moves from approval into controlled delivery.

It should not be completed in isolation by the project team. The quality of the document depends on structured engagement with operational stakeholders and named benefit owners.

When using this template:

- Start with the benefits approved in the Business Case. Do not introduce new justification without formal change control.

- Engage operational leaders early to confirm ownership and measurement feasibility.

- Establish baselines before implementation wherever possible.

- Align benefit timing with delivery milestones and operational transition.

- Apply governance discipline to assumptions, measurement and reporting.

This document should be reviewed and updated:

- At major stage boundaries

- When scope materially changes

- When strategic context shifts

- When benefit forecasts require revision

The purpose of this template is not to create additional documentation. It is to ensure that promised value is defined, owned and measurable before delivery proceeds.

## Governance Context

The Benefits Management Strategy is the formal document that governs how value will be realised from an approved investment.

It sits alongside the PID and complements the Business Case.
The Business Case explains why the investment is justified.
The Benefits Management Strategy explains how value will be structured, owned, measured and controlled.

The template below provides a high-authority structure suitable for controlled governance environments.

## 2.1 Executive Summary

This section should summarise:

- The purpose of the investment.

- The total number of approved benefits.

- The expected value and timescale of realisation.

- The governance structure for ownership and reporting.

It should clearly state that the Senior Responsible Owner remains accountable for benefit realisation.

Purpose

To provide senior decision makers with a concise and defensible overview of the benefits framework without requiring detailed review of supporting sections.

Drafting Guidance

- Summarise the total number of benefits and their aggregate expected impact.

- Confirm linkage to the approved Business Case.

- Identify the overall realisation timeframe.

- Confirm named accountability at SRO and benefit owner level.

- Highlight any significant dependencies or constraints.

Quality Checks

- Is the summary consistent with detailed benefit profiles?

- Is the aggregate value evidence based?

- Are timeframes realistic?

- Is accountability explicit?

Common Weakness

Executive summaries that restate aspirations rather than governance commitments.

Prompt

If this section were read in isolation, would it demonstrate controlled accountability for value?

## 2.2 Strategic Context and Link to the Business Case

This section confirms:

- The strategic objectives the project supports.

- The specific benefits approved in the Business Case.

- Any constraints or assumptions agreed at approval.

Each benefit should be traceable to a strategic objective.

This section establishes that the Benefits Management Strategy is not creating new justification.

Purpose

To demonstrate that benefits remain aligned with the approved investment rationale and have not drifted from their original justification.

Drafting Guidance

- Reference the approved Business Case version and date.

- Map each benefit to a stated strategic objective.

- Confirm any assumptions agreed at approval stage.

- Identify constraints carried forward from the Business Case.

- Confirm that no new justification is being introduced.

Quality Checks

- Are strategic references specific and documented?

- Is traceability between benefit and objective clear?

- Have material changes since approval been identified?

Common Weakness

Benefits reframed post approval without formal change control.

Prompt

Can an independent reviewer trace this benefit directly back to the approved Business Case?

## 2.3 Benefits Overview and Categorisation

Provide a structured summary of all benefits, typically categorised as:

- Financial or cashable

- Non financial or service improvement

- Compliance or risk reduction

- Efficiency or productivity

- Qualitative or reputational

A summary table should include:

- Benefit reference

- Benefit description

- Benefit owner

- Baseline value

- Target value

- Target date

- Measurement method

This gives reviewers immediate visibility of control and structure.

Purpose

To provide structured visibility of all approved benefits in a consolidated and governance-ready format.

Drafting Guidance

- Categorise benefits consistently and avoid duplication.

- Ensure each benefit has a unique reference identifier.

- Present baseline and target values clearly.

- Confirm ownership is named at operational level.

- Include measurement method for each benefit.

Quality Checks

- Are benefits materially distinct?

- Are categories meaningful rather than cosmetic?

- Is each benefit measurable or realistically assessable?

- Are financial and non-financial benefits clearly differentiated?

Common Weakness

Long lists of overlapping benefits presented without prioritisation or structure.

Prompt

If two benefits appear similar, should they be consolidated into a single measurable outcome?

## 2.4 Benefit Profiles

Each significant benefit should have a detailed profile including:

- Description of the benefit

- Strategic objective supported

- Baseline performance level

- Target performance level

- Measurement indicator

- Data source

- Frequency of measurement

- Assumptions

- Dependencies

- Risks to realisation

- Named benefit owner

- Date expected to be realised

Profiles may be included within the document or annexed.

Purpose

To define each material benefit in sufficient depth to withstand scrutiny and enable structured tracking.

Drafting Guidance

- Clearly describe the outcome, not the activity.

- Define baseline and target values using objective data.

- Identify assumptions and dependencies explicitly.

- Assign a named operational benefit owner.

- Include expected realisation date and review frequency.

Quality Checks

- Is the benefit outcome-focused rather than task-based?

- Are data sources credible and auditable?

- Are assumptions transparent?

- Is ownership realistic and senior enough?

Common Weakness

Benefit profiles describing project outputs rather than operational outcomes.

Prompt

If the project delivers successfully, what operational change must occur for this benefit to materialise?

## 2.5 Governance Structure and Accountability

This section defines:

- The Senior Responsible Owner

- Benefit owners

- Reporting responsibilities

- Escalation routes

- Relationship to project board or programme governance

It should clarify:

- Who owns delivery outputs

- Who owns operational change

- Who owns benefit measurement

- Who approves sign off

Governance must be explicit.

Purpose

To make responsibility for value explicit and defensible under formal review.

Drafting Guidance

- Identify the Senior Responsible Owner.

- Name each operational benefit owner.

- Define reporting routes and escalation thresholds

- Clarify separation between delivery accountability and benefit accountability

- Confirm sign-off authority.

Quality Checks

- Is accountability assigned to individuals, not groups?

- Are escalation routes defined?

- Is operational leadership engaged?

- Is SRO responsibility explicit?

Common Weakness

Generic governance diagrams without named individuals or defined authority.

Prompt

If a benefit underperforms, who has the authority to intervene?

## 2.6 Measurement and Baseline Approach

This section sets out:

- How baseline data has been established

- How measurement will be conducted

- Data collection methods

- Tools or systems used

- Validation mechanisms

It should confirm that benefits are measurable or realistically assessable.

Without a clear baseline methodology, benefits cannot be evidenced.

Purpose

To ensure that benefit claims can be evidenced through objective and repeatable measurement.

Drafting Guidance

- Define the baseline measurement point.

- Identify data source and collection method.

- Confirm measurement frequency.

- Describe validation or audit mechanism.

- State any data limitations.

Quality Checks

- Is the baseline documented and dated?

- Can measurement be independently verified?

- Are assumptions clearly recorded?

- Is measurement proportionate to materiality?

Common Weakness

Benefits described as improvement without documented starting position.

Prompt

What independent evidence confirms the baseline from which improvement is claimed?

## 2.7 Benefits Realisation Schedule

This section provides a structured timeline showing:

- When each benefit is expected to begin

- When it is expected to reach target level

- Links to project milestones

- Links to operational transition

This may be presented as a schedule or phased table.

Benefits must align with delivery sequencing.

Purpose

To align benefit timing with delivery sequencing and operational transition.

Drafting Guidance

- Link each benefit to relevant delivery milestone.

- Identify when measurement will begin.

- Define expected ramp-up period.

- Clarify whether benefits are one-off or recurring.

- Align schedule with stage boundaries.

Quality Checks

- Is timing realistic given operational readiness?

- Are early “quick wins” credible?

- Are long-term benefits supported by sustained capability?

- Is the schedule consistent with the delivery plan?

Common Weakness

Benefits forecast to materialise before operational adoption is feasible.

Prompt

What operational condition must exist before this benefit can begin to accrue?

## 2.8 Resource and Capability Requirements

This section defines:

- Required operational changes

- Training requirements

- Additional staffing or capacity

- Technology enablement

- Budget implications

It should confirm that sufficient capability exists to realise benefits after delivery.

Realisation without resource is not credible.

Purpose

To confirm that operational capacity exists to convert outputs into measurable value.

Drafting Guidance

- Identify required process changes.

- Confirm training or capability development needs.

- Specify additional staffing if required.

- Identify funding implications beyond delivery.

- Confirm operational readiness.

Quality Checks

- Is resource formally allocated?

- Are skills gaps acknowledged?

- Is ongoing monitoring funded?

- Is operational leadership committed?

Common Weakness

Assuming behavioural or process change without resourcing it.

Prompt

What operational investment is required to enable this benefit after go live?

## 2.9 Communications and Reporting Framework

This section defines:

- Reporting frequency

- Report format

- Audience for reporting

- Integration with board reporting cycles

- Mechanism for highlighting underperformance

Benefits reporting must be structured and predictable.

Purpose

To embed benefits governance within formal reporting and oversight mechanisms.

Drafting Guidance

- Define reporting frequency.

- Identify report recipients.

- Align reporting with board cycle.

- Define escalation process for underperformance.

- Confirm record keeping and audit trail.

Quality Checks

- Is reporting periodic and structured?

- Are underperformance triggers defined?

- Is reporting integrated with project governance?

- Is there visibility at senior level?

Common Weakness

Benefits monitored informally without structured board visibility.

Prompt

If a benefit fails to meet target for two reporting cycles, what formally happens next?

## 2.10 Risk and Dependency Assessment

This section identifies:

- Risks to benefit achievement

- Interdependencies between benefits

- External dependencies

- Mitigation strategies

Benefit level risk should align with the project risk log but remain explicitly visible within this strategy.

Purpose

To ensure that threats to benefit realisation are identified and actively managed.

Drafting Guidance

- Identify risks specific to benefit achievement.

- Map dependencies across programmes or external actors.

- Align with project risk log but maintain benefit-level visibility.

- Define mitigation and monitoring actions.

- Assign risk ownership.

Quality Checks

- Are benefit-level risks distinct from delivery risks?

- Are dependencies explicit?

- Are mitigations realistic?

- Is ownership defined?

Common Weakness

Assuming benefits will materialise if the project delivers, without analysing realisation risk.

Prompt

What could prevent this benefit from being realised even if delivery is technically successful?

## 2.11 Updating and Change Control

Benefits may change if:

- Scope changes

- Assumptions prove invalid

- Targets become unrealistic

- External conditions shift

This section defines:

- How benefits will be reviewed

- How revisions are approved

- How changes are recorded

- How alignment to the Business Case is maintained

Benefits governance must evolve in a controlled manner.

A properly structured Benefits Management Strategy ensures that:

- Value is defined before delivery begins

- Ownership is explicit

- Measurement is structured

- Governance continues beyond project closure

The document is not an administrative exercise.
It is the control mechanism for ensuring that promised outcomes are realised.

Purpose

To maintain alignment between benefits, strategic objectives and approved investment decisions over time.

Drafting Guidance

- Define formal review intervals.

- Specify approval authority for benefit changes.

- Record revisions and rationale.

- Confirm alignment with Business Case.

- Maintain version control.

Quality Checks

- Are changes documented and approved?

- Is strategic alignment revalidated?

- Are revised targets justified?

- Is audit trail maintained?

Common Weakness

Benefits redefined informally without governance approval.

Prompt

If a benefit target must be revised, who approves the change and how is it recorded?

# Part 3. Benefits Realisation and Review Report Template

## How to Use the Benefits Realisation and Review Report

This report provides structured accountability for value during and after delivery.

It should be produced:

- At defined reporting intervals

- At stage boundaries

- Following go live

- At project closure

- At agreed post-implementation review points

The report must be evidence-based. Narrative without measurement undermines credibility.

When completing this report:

- Use current, dated measurement data.

- Quantify variance wherever possible.

- Identify root causes rather than symptoms.

- Define corrective actions clearly and assign ownership.

- Escalate material underperformance in accordance with governance thresholds.

Benefits realisation often continues beyond project closure. Where this is the case, the report must clearly state who retains accountability and how measurement will continue within operational governance.

This document protects the integrity of the original investment decision.

## Governance Purpose

The Benefits Realisation and Review Report provides formal assurance that value has been delivered, is being delivered, or requires corrective action.

It is used during and after delivery to confirm whether approved benefits are being realised in line with the Benefits Management Strategy.

## 3.1 Report Overview

This section should summarise:

- Reporting period

- Project or programme reference

- Current status of overall benefit realisation

- Key areas of over or under performance

- Escalations or corrective actions required

The overview should give senior decision makers a clear picture of value performance without requiring detailed analysis.

Purpose

To provide senior governance bodies with a clear and evidence-based summary of benefit performance during the reporting period.

Evidence Required

- Reporting period covered.

- Overall status of benefit realisation.

- Summary of material variances.

- Escalations or decisions required.

- Confirmation of continued SRO accountability.

Quality Checks

- Is the status evidence-based rather than narrative?

- Are material risks clearly highlighted?

- Is overall value impact quantified where possible?

- Are decisions required clearly stated?

Escalation Trigger

Material deviation from target or timing beyond agreed tolerance must be escalated to the SRO and board.

## 3.2 Benefits Performance Summary

Provide a consolidated table showing:

- Benefit reference

- Benefit description

- Baseline value

- Target value

- Current measured value

- Variance

- Status indicator

- Benefit owner

This table provides immediate transparency.

Benefits should be categorised as:

- Achieved

- On track

- At risk

- Underperforming

- Not yet measurable

Status indicators should be evidence based, not subjective.

Purpose

To provide a consolidated, measurable view of performance against approved targets.

Evidence Required

- Baseline value.

- Target value.

- Current measured value.

- Variance (numerical or qualitative).

- Named benefit owner.

- Status category with justification.

Quality Checks

- Are measurements current and dated?

- Is status supported by data?

- Are recurring benefits clearly distinguished from one-off gains?

- Are financial impacts reconciled where relevant?

Escalation Trigger

Any benefit categorised as “Underperforming” for two consecutive reporting cycles must trigger corrective action review.

## 3.3 Variance Analysis

For benefits that are:

- Underperforming

- Delayed

- No longer achievable

Provide structured explanation including:

- Cause of variance

- Impact on overall value

- Assumptions that proved incorrect

- Dependencies not met

- Operational constraints encountered

This section should demonstrate analysis, not defensiveness.

Purpose

To explain material deviation from approved targets and protect governance credibility.

Evidence Required

- Quantified variance.

- Root cause analysis.

- Assumptions that proved incorrect.

- Dependencies or constraints impacting delivery.

- Impact on aggregate benefit value.

Quality Checks

- Is the root cause clearly identified?

- Is responsibility acknowledged?

- Is analysis factual rather than defensive?

- Is impact on overall value transparent?

Escalation Trigger

Variance exceeding agreed tolerance requires formal recovery plan approval.

## 3.4 Remedial Action and Recovery Plan

Where benefits are at risk or underperforming, define:

- Corrective actions

- Responsible owner

- Revised timescales

- Escalation route if recovery fails

If targets require revision, this must be explicitly recorded and approved through governance channels.

Purpose

To demonstrate active management of underperforming or delayed benefits.

Evidence Required

- Defined corrective actions.

- Named action owner.

- Revised timescales.

- Resource implications.

- Revised target where necessary.

- Approval record for any target adjustment.

Quality Checks

- Are actions realistic and resourced?

- Is accountability clear?

- Are revised targets justified?

- Has change control been applied formally?

Escalation Trigger

Failure to implement agreed recovery actions within defined timeframe must be reported to the governance board.

## 3.5 Emerging or Secondary Benefits

Projects may generate additional outcomes not originally forecast.

This section should:

- Identify any new measurable benefits

- Confirm whether they align with strategic objectives

- Confirm whether they will be tracked formally

Emerging benefits should not replace or distract from approved commitments.

Purpose

To record additional measurable value arising from the investment without undermining original commitments.

Evidence Required

- Description of new benefit.

- Strategic objective alignment.

- Baseline and measurement method.

- Confirmation of ownership.

- Confirmation that approved benefits remain primary focus.

Quality Checks

- Is the new benefit material and measurable?

- Does it align with strategic objectives?

- Is ownership confirmed?

- Is there risk of distraction from approved commitments?

Escalation Trigger

Emerging benefits that materially alter the value profile should be reviewed under formal governance.

## 3.6 Strategic Alignment Confirmation

Confirm whether:

- The original strategic objectives remain valid

- The realised benefits continue to support those objectives

- Any external policy or organisational changes have altered priorities

If strategic context has changed, this should be noted and formally reviewed.

Purpose

To confirm that realised benefits continue to support current organisational strategy.

Evidence Required

- Confirmation of strategic objective alignment.

- Identification of policy or organisational changes.

- Statement on continued relevance of benefits.

Quality Checks

- Has strategic context changed since approval?

- Do benefits still support priority outcomes?

- Is any revalidation required?

Escalation Trigger

Material change in strategic direction may require Business Case refresh or formal review.

## 3.7 Risk and Dependency Update

Provide an updated summary of:

- Risks to ongoing benefit realisation

- Dependencies affecting performance

- Mitigation status

This ensures benefit governance remains active beyond initial reporting.

Purpose

To maintain visibility of ongoing threats to benefit realisation.

Evidence Required

- Updated risk summary specific to benefits.

- Dependency status update.

- Mitigation actions and ownership.

- Residual risk assessment.

Quality Checks

- Are benefit-level risks distinguished from project risks?

- Are mitigations active and monitored?

- Is risk ownership assigned?

- Are emerging risks recorded promptly?

Escalation Trigger

High-risk exposure to material benefits requires board-level visibility.

## 3.8 Post Closure Accountability

Where the project has formally closed, confirm:

- Which benefits continue to be measured

- Who retains accountability

- Reporting frequency

- Date of final sign off

Benefits often mature after delivery completion. Governance must not end at closure.

Purpose

To confirm governance continuity where benefits extend beyond project delivery.

Evidence Required

- List of ongoing benefits post closure.

- Named accountable operational owner.

- Reporting frequency.

- Expected final sign-off date.

- Integration into operational performance reporting.

Quality Checks

- Has accountability transferred formally?

- Is measurement embedded in business-as-usual systems?

- Is final review date defined?

Escalation Trigger

Failure to embed ongoing measurement into operational governance requires senior review.

## 3.9 Formal Sign Off

This section confirms:

- Whether benefits have been realised in line with approved targets

- Whether remedial action remains active

- Whether strategic objectives have been satisfied

Signed by:

- Senior Responsible Owner

- Operational Benefit Owner

- Finance Representative where applicable

Formal sign off provides governance closure and evidential record.

The Benefits Realisation and Review Report ensures that:

- Value is measured, not assumed

- Underperformance is visible

- Accountability is maintained

- Investment decisions can withstand retrospective scrutiny

It completes the value lifecycle that began with the Business Case.

### Purpose

To provide documented confirmation of value realisation under accountable governance.

Evidence Required

- Summary of benefit performance against targets.

- Confirmation of any outstanding actions.

- Declaration of strategic objective satisfaction.

- Signed confirmation by SRO and benefit owners.

Quality Checks

- Is sign off evidence based?

- Are residual risks acknowledged?

- Is there audit trail for future review?

Escalation Trigger

Benefits not fully realised at closure must be formally transferred with documented accountability.

# Annex A. Using AI Responsibly When Drafting Benefits Governance Documentation

Artificial intelligence tools can support drafting and structuring benefits documentation. They do not replace evidence gathering, stakeholder engagement or accountable judgement.

AI may assist with:

- Structuring benefit profiles

- Refining wording for clarity

- Generating measurement indicators

- Creating summary tables

- Drafting variance analysis narratives

AI must not be used to:

- Invent baselines or performance data

- Fabricate measurement evidence

- Assign ownership without confirmation

- Estimate financial value without validated modelling

- Replace stakeholder consultation

When using AI to support drafting:

- Define the context clearly
Specify the approval stage, project scope, and strategic objectives.

- Provide evidence
Input baseline data, workshop outputs, risk summaries and stakeholder notes. Do not ask AI to create unsupported assumptions.

- Specify the role
Example: “You are drafting a Benefits Management Strategy for a public sector project operating under formal governance scrutiny.”

- Review critically
Treat output as a draft. Validate data sources, assumptions and alignment to approved documentation.

- Maintain accountability
The Senior Responsible Owner and named benefit owners remain accountable for accuracy and realism.

AI can improve structure and clarity.
It cannot defend benefit claims under scrutiny.

Governance responsibility remains human.