# Project Governance Status Report

A Practitioner Guide and Board Facing Template

Author

James J. Bailey

Project Management and Business Case Advisory

Connect on LinkedIn

https://www.linkedin.com/in/jamesbailey-uk/

# Part 0. Where the Status Report Sits in the Governance Architecture

Projects are not controlled by activity reporting. They are controlled by delegated authority within defined tolerances.

Under a structured delivery model, the Project Board approves the Business Case and sets explicit tolerance boundaries for time, cost, scope, risk and benefit performance. The Project Manager is authorised to deliver within those boundaries. Control escalates only when a breach is forecast.

The Status Report exists to preserve that delegation.

It is the formal mechanism by which the Project Manager demonstrates that delivery remains viable, forecast performance remains within tolerance and the Business Case remains protected. It is therefore not administrative reporting. It is delegated authority in written form.

Within the wider control system, reporting operates alongside planning, risk management and stage control. Planning sets intent. Risk management manages uncertainty. The Status Report confirms whether those mechanisms are functioning as designed.

It also provides early warning.

Mature governance environments do not fail because of unforeseen events. They fail because deterioration is not surfaced early enough for correction. The Status Report is the structured opportunity to expose drift before it becomes exception.

This document sits between the Project Manager and the Project Board. It is not a team progress update and it is not a portfolio dashboard. It is the control interface at project board level.

When written properly, it demonstrates three things:

- Forecast discipline

- Tolerance awareness

- Delivery judgement

When written poorly, it disguises drift behind narrative.

This guide ensures the former.

# Part 1. What Project Boards Actually Look For

Boards do not read Status Reports for interest. They read them for assurance.

The first question in a board member’s mind is simple:
“Are we still in control?”

Control is not measured by how much activity has taken place. It is measured by whether forecast performance remains within agreed limits and whether emerging threats are visible.

A Board reviewing a Status Report is typically assessing five underlying dimensions.

1. Tolerance Exposure

They want explicit confirmation that time and cost forecasts remain within delegated limits. If tolerance margins are tightening, they expect to see this stated clearly. Silence is interpreted as weakness.

2. Forecast Credibility

Boards are experienced at detecting vague optimism. A credible report links commentary to forecast movement. It explains why confidence is high, stable or reducing. It acknowledges uncertainty without exaggeration.

3. Trend, Not Snapshot

Green status without context is meaningless. Boards look for direction of travel. Is performance stabilising? Improving? Gradually eroding? Strong reports describe trajectory, not just colour coding.

4. Risk Exposure and Material Issues

Boards do not require full registers. They require visibility of material exposure. They want to know which uncertainties threaten tolerance and how they are being managed. Emerging exposure should be surfaced early, not hidden until escalation.

5. Clarity of Escalation

If support or direction is required, the Board expects this to be stated directly. Indirect signalling undermines control.

Weak reports share common patterns:

- Activity heavy but judgement light

- RAG ratings unsupported by narrative

- Risk lists without prioritisation

- No explicit comparison to tolerance

- No clear statement of delivery confidence

Strong reports are shorter but sharper. They are explicit about exposure. They show forecast awareness. They demonstrate professional judgement.

That is the standard this template is built to support.

# Part 2 – The Project Status Report Template

How to Use This Template

This template is designed for routine reporting from the Project Manager to the Project Board within a manage by exception framework.

It should normally be concise, typically two to three pages. If it becomes longer, focus has usually shifted from governance to operational detail.

Before drafting, confirm:

- Current tolerance levels

- Latest approved baselines

- Most recent risk and financial forecasts

- Any board decisions already pending

When writing:

- Anchor commentary to forecast, not activity

- Compare explicitly against tolerance

- Provide narrative explanation for movement

- Avoid duplicating full registers

- Remove instructional prompts before submission

The final document should read as evidence of control, not administrative compliance.

## 2.1 Executive Snapshot

The Executive Snapshot provides immediate governance clarity. It is not decorative; it is diagnostic.

This section should state clearly whether the project remains within delegated tolerances and whether delivery confidence has changed since the previous reporting cycle. The Board should be able to understand the overall health of the project within one minute of reading.

Avoid vague reassurance such as “progressing well” or “on track.” Instead, provide a short paragraph explaining the current position, any movement in tolerance margin, and whether exposure is stable, improving or tightening.

If delivery confidence has reduced, say so and explain why. Boards value early transparency more than delayed optimism.

This section establishes professional credibility.

## 2.2 Forecast Against Tolerances

This is the core control section of the report.

The purpose is to demonstrate that the Project Manager understands the current forecast position relative to the limits approved in the PID or Stage Plan.

For time and cost, compare baseline, current forecast and tolerance explicitly. If contingency is being consumed, explain the rate and underlying drivers. If recovery action is underway, describe its likely effect on forecast stability.

For scope and benefits, confirm whether the underlying assumptions of the Business Case remain intact. If material assumptions have shifted, explain the governance impact.

This section must be analytical, not descriptive. It demonstrates control discipline and forecast maturity.

## 2.3 Milestone Position

Milestones reveal trajectory more clearly than narrative commentary.

Provide a structured table showing baseline dates, current forecast dates and variance. Then accompany that table with a paragraph explaining the significance of any movement.

If a milestone has slipped but remains within tolerance, explain the recovery strategy. If margin is narrowing, state that clearly.

The Board should understand whether the delivery path remains stable or whether drift is emerging.

This section should never hide deterioration behind operational language.

## 2.4 Risk and Material Issue Position

This section summarises exposure that may threaten tolerance.

Do not reproduce the full risk register. Instead, identify the material risks and realised issues that affect viability, timing, cost or confidence.

For each item, explain residual exposure after mitigation and whether further escalation is likely. Where a realised risk has become an issue, clarify how it is being controlled and whether it affects forecast tolerance.

The objective is to demonstrate that uncertainty is being actively managed and that no material exposure is being concealed.

Strong reporting in this section reinforces trust between Project Manager and Board.

## 2.5 Financial Position

Financial reporting should be clear, proportionate and forward looking.

State approved budget, actual expenditure to date, forecast at completion and remaining contingency. Explain any variance drivers and whether contingency consumption remains proportionate to stage maturity.

If cost variance remains within tolerance but trending unfavourably, say so. Financial drift is best managed early.

The Board is not looking for accounting detail. It is looking for assurance that financial control remains deliberate.

## 2.6 Decisions and Support Required

This section formalises escalation where required.

If no decision is required, confirm that explicitly. Silence can be misinterpreted.

If support or direction is required, structure the request clearly. State the decision sought, the rationale, the impact if not approved and the timeframe within which the decision is required.

This clarity prevents passive governance and reinforces disciplined escalation.

## 2.7 Forward Look

The Forward Look is a short trajectory statement.

It should identify the key focus for the next reporting period, anticipated risk movement, critical dependencies and whether delivery confidence is expected to change.

Avoid listing tasks. Instead, provide a professional judgement of how the project is likely to evolve over the next cycle.

This closes the governance loop between forecast and action.

# Part 3. Board-Level Project Status Report Template

| Section 1 – Executive Snapshot |  |  |  |
| --- | --- | --- | --- |
| Project Title |  | Reporting Period | Current Stage |
| Status Panel |  |  |  |
| Overall RAG: Green / Amber / Red | Delivery Trend: Improving / Stable / Deteriorating | Delivery Confidence: High / Medium / Low | Tolerance Position: Within / Forecast Breach |
| Executive Position Statement |  |  |  |
| Provide a concise but substantive overview of current health. Confirm tolerance position. Explain movement since last report. State viability clearly |  |  |  |

| Section 2 – Forecast Against Tolerances |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Time and Cost Table |  |  |  |  |  |
| Performance Dimension | Baseline | Current Forecast | Tolerance Range | Variance | Status |
| Time |  |  |  |  |  |
| Cost |  |  |  |  |  |
| Resource Capacity |  |  |  |  |  |

| Section 3 – Milestone Position |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Baseline Date | Current Forecast | Variance | Commentary |

| Section 4 – Risk and Material Issue Position |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Overall Risk Exposure Trend |  |  |  |  |  |
| Stable / Increasing / Reducing – short explanation |  |  |  |  |  |
| Key Risks Table |  |  |  |  |  |
| Risk ID | Description | Residual Exposure | Owner | Mitigation Status | Escalation Risk |
| Material Issues Table |  |  |  |  |  |
| Issue ID | Description | Impact | Owner | Resolution Plan | Board Attention Required |

| Section 5 – Financial Summary |  |  |  |  |
| --- | --- | --- | --- | --- |
| Budget Approved | Actual to Date | Forecast at Completion | Remaining Contingency | Variance |
| Financial Commentary Box |  |  |  |  |
| Commentary: Explain variance drivers and contingency trend |  |  |  |  |

| Section 6 – Decisions and Support Required |  |  |  |
| --- | --- | --- | --- |
| Decision Required | Rationale | Impact if Not Approved | Required By |
| If none required: |  |  |  |
| Statement: No Board decision required at this reporting point |  |  |  |

Section 7 – Forward Look

Forward View: Describe next period focus, critical dependencies, expected confidence movement