## REGISTER
Name of the owning Strand or Programme. | Name of the Project or Study at Risk. | Reference Number of the Project or Study at risk. | Sequentially allocated unique identifier. | Name of the person who raised the risk. | The date on which the risk was raised. | Current status of the risk. One of: Open. Closed. Transferred, Accepted | Current RAG status of the risk. Determined using Proximity, Probability and Impact to access the relevant RAG Matrix | The likelyhood of the risk being realised. One of: Very Low. Low. Medium. High. Very High | The effect that the realisation of the risk would have. One of: Very Low. Low. Medium. High. Very High | Date to indicate the potential timing of the risk (i.e. whether it is immediate or likely to occur at some point in the future). If risk is immediate then set same as Date Raised, else set to a future date. This date, along with Probability and Impact, is used to determine RAG Status. | This must be clearly stated in terms of cause and effect along the lines of 'There is a risk of/that…..which may result in……..'. | A more comprehensive desription of the impact if this is required. | Used in conjunction with Proximity. If the risk will only manifest itself, or grow stronger, due to some future event or cuircumstance then details should be recorded. | The initial level of management for the risk. One of: Board. Project | The current level of management for the risk. At creation it should be set same as Original Level. Over time, it will indicate escalation or demotion when compared to Original Level. | Name of person responsible for managing the risk | A list of the mitigating actions that could be taken in response to the risk. | The selected action(s) to be taken. This must be completed at creation even if the only known action at the time is to further analyse the risk to identify possible responses. | Name(s) of individual(s) responsible for implementing action(s). | A succinct description of current progress toward completion of action(s) | Date on which the Register entry was last updated. | Target date for completion of Chosen Action. | To maintain audit trail to Issue Register. If the risk orginated as an issue then record the original Issue Number. If the risk is transferred to the Issue Register then record the resulting Issue Number. | Date on which the risk is closed or transferred to issue | Estimated cost of mitigation activities. | Probability of risk occuring expressed as a percentage. | Budget calculated as Mitigation Cost * %Likelihood
Strand / Programme | Project/Study Name | Project ID Number | Risk Number | Raised By | Date Raised | Risk Status | RAG Status | Probability | Impact | Proximity | Description of Risk | Impact Description | Trigger | Original Level | Current Level | Risk Owner | Possible Mitigating Actions | Chosen Mitigating Action | Action Owner | Action Status | Date of Last Update | Action Target Date | Issue Number | Closure Date | Mitigation Cost | % Like- lihood | Risk Budget | RAG Status Calculation Fields
Enter the Name of the Strand or Programme | Enter the Name of The Project | Enter the Project Number | Enter the Risk ID | Enter the Name of the Person that Rasied the Risk (Using their email address adds a useful means contact) | Enter the Date the Risk was Raised | Enter the Status of the Risk, Open, Closed or Transferred. (In this template the options are secleted on a list of RAG MATRIX.) | This is calculated from the BRAG Matrix. BRAG Should be either Red, Amber, Green or Blue (complete) | The likelihood of the risk being realised, one of: VERY LOW, LOW, MEDIUM, HIGH, VERY HIGH. (In this template the options are secleted on a list of RAG MATRIX.) | The effect that the realisation of the risk would have, one of: VERY LOW, LOW, MEDIUM, HIGH, VERY HIGH. (In this template the options are secleted on a list of RAG MATRIX.) | A date to indicate the potential timing of the risk (format dd/mm/yy or mmm-yy), i.e. whether the risk is immediate or likely to occur at some point in the future. | (IF) This must be clearly stated in terms of cause and effect along the lines of 'There is a risk of/that……………..which may result in…………….' | (THEN) A more comprehensive description of Impact if this is required. | Used in conjunction with Proximity. If the risk will only manifest itself, or will grow stronger, due to some future event or circumstance then details should be recorded. | Enter the initial level that the Risk was Rasied i.e. Project | The the current level at which the risk is being managed i.e. Programme | Name of individual responsible for managing the risk. | A list of possible actions that could be taken in response to the risk. | The selected action(s) to be taken. This field must be completed at Creation even if the only known action at that time is to further analyse the risk to determine possible responses. | Name(s) of individual(s) responsible for implementing action(s). | A succinct description of the current progress towards completion of action(s). Naming and Dating Action Status is useful when there are a number for resources mitigating the risk. | Date on which the risk entry was last updated. | Target date for completion of Chosen Action (format dd/mm/yy). | To maintain an audit trail to the Issue Register. If the risk originated as an Issue then record the original Issue Number. If the risk is transferred to the Issue Register then record the resulting Issue Number. | The date on which the risk is CLOSED or TRANSFER TO ISSUE (format dd/mm/yy). | Used in conjunction with Mitigation Cost. This is the Probability of the risk expressed as a % for budgeting purposes. | Used in conjunction with Mitigation Cost. This is the Probability of the risk expressed as a % for budgeting purposes. | To hold the result of Mitigation Cost X % Likelihood to give a provision for treating the risk. If a calculation is done for all known risks on a project then the total provides a budget provision for the treatment of risk for the whole of the project. | #VALUE! | #VALUE! | #VALUE!
Data Collection | Secure Data Collection (SDC) | N00DC050 | R001 | JamesLeal@ProjectTemplates.net | 2013-02-05 | OPEN | AMBER | Low | Low | 2013-03-01 | There is a risk that Specific BA resource will move to another project, resulting in sections of BRS not being completed | Ensure complete handover and knowledge transfer takes place. Business Requirement Specification must be signed off prior to handover | New Project Mandate may be approved sooner that estaimated | Project | Programme | James Leal | NA | Ensure replacement BA resource secured. | FirstName.LastName@email.com | New BA identified with DC knowledge. Handover in progress - James Leal 2013 02 05 | 2013-02-05 | 2013-02-22 | NA | 2013-02-10 | 1000 | 100% | 1000 | 1900-01-23 | <1 | LowLow<1
Data Collection | Secure Data Collection (SDC) | N00DC050 | R002 | JamesLeal@ProjectTemplates.net | 2013-02-06 | TRANSFER TO ISSUE | BLUE | Medium | High | 2013-02-05 | The is a risk that the Governanace process may ask for late changes. Thelevel of project governance needs to be agreed. What products are expected. What gateways etc. | No project Brief, Business Case or Charter are available. Delay in project initiation. No Supporting documentation for the Work Orders which may delay approval and initiation. | NA | Project | Programme | James Leal |  | Agree with Programme Support Office, methodology and level of governance. | FirstName.LastName@email.com | Raised as Issue and Progress will be captured in the Isuue Register. James Leal 2013 02 27 | 2013-02-27 | 2013-02-27 | I021 | 2013-02-27 | NA | 60% | NA | -22 | <1 | MediumHigh<1
Transformation | Data Migration | Z0003242 | R023 | JamesLeal@ProjectTemplates.net | 2012-03-15 | OPEN | AMBER | Medium | Medium | 2013-08-15 | US Bank SBC Citrix IBM Proof of Concept (POC) - Application Performance (If...) US Bank have (not) identified and engaged onshore and offshore users to then complete application performance testing using the Banking SBC Citrix POC farm within the IBM datacentre by 17th August 2012. | (Then...) The US Bank SBC Citrix POC in the IBM datacentre will not be completed as per USB-03b Schedule and forecast dates (& Level 3/Level 2/Leve 1 milestones) outlined with the most recent USB-03b Transformation Change Request. |  | Workstream | WorkStream | First Last Name |  | JL 02/08/2012: At weekly meeting, Name & Name confirmed that US Bank will start user testing of apps week commencing 8th August. Focus being user experience and performance of service and application (as the POC environment is hosted in IBM Datacentre). Action from meeting: Name to work with offshore contacts to identify offshore testers and forward details to Project. Total concurrent users revised to approximately 10-20. ONGOING. | FirstName.LastName@email.com | JL 02/08/2012: At weekly meeting, Name & Name confirmed that US Bank will start user testing of apps week commencing 8th August. Focus being user experience and performance of service and application (as the POC environment is hosted in IBM Datacentre). NAME 04/08/2012: See Assumption a012 and Risk r007 (referencing original POC date) for full history and background. New Assumption (a013) raised to reflect new POC completion date. New Risk (r008) raised to reflect new POC completion date. | 2012-08-02 | [6 empty] | 1901-01-12 | >3 | MediumMedium>3
Transformation | Life & Pensions | Z0001234 | R66 | JamesLeal@ProjectTemplates.net | 2013-06-06 | OPEN | RED | Medium | High |  | If LIFE comes into scope via the appropriate change request mechanism | Then the requirements gathering, analysis, service definition and impact analysis would need to be conducted across the configuration management areas of the business increasing the man hours required for the work packets. In addition a dedicated solution may have to be provided in place of the current leveraged service. |  | Project | WorkStream | James Leal |  | Present the options to the Project Board of extending the timescales for delivery and/or assigning additional resources to the project. | JL | 13.06.13 JL: Changed action today to accurately reflect the PMP 20.06.13 JL: Software sales, the product team in the US and the Life client director are working together to build a dedicated PoC environment to be stood up ASAP. No dates known at this time. A decision as to a scope change will not be made until a successful PoC has been completed. 27.06.13 JL: Meeting booked with CTO and key stakeholder to confirm LIFE is currently not in scope of this project as some had assumed it was. 04.07.13 JL: Subsequent meeting with sponsors and one key stakeholder resulted in packaging being in scope with LIFE or A.N.Other tool. Raising as an issue | 2013-07-04 | [6 empty] | -41459 | <1 | MediumHigh<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[6 empty] | OPEN | AMBER | Low | Low | [18 empty] | 0 | <1 | LowLow<1
[25 empty] | 0 | 0 |  | 0 | <1 | <1
Formulas:
RAG Status Calculation Fields = ([Proximity]-[Date of Last Update])

## NOTES
Field | Description | Reference Documents / Notes
Strand / Programme | The owning Strand or Programme
Project/Study Name | Name of the Project/Study at risk
Project ID Number | Reference Number for the Project/Study at risk .
Project ID | The Project ID for the Project/Study at Risk .
Risk Number | Unique identifier, allocated sequentially.
Raised by | Name of individual who raised the risk.
Date Raised | Date on which the risk was raised (format dd/mm/yy).
Risk Status | The status of the register entry, one of:
OPEN
CLOSED
TRANSFER TO ISSUE
RAG Status | Current RAG status of the actual risk. Automatically determined from the RAG MATRIX using a combination of Probability, Impact and Proximity. | See RAG MATRIX GRAPHIC sheet for visual representation of table held in RAG MATRIX sheet.
Probability | The likelihood of the risk being realised, one of: | See GUIDANCE sheet for explanation of standard evaluation criteria .
VERY LOW
LOW
MEDIUM
HIGH
VERY HIGH
Impact | The effect that the realisation of the risk would have, one of: | See GUIDANCE sheet for explanation of standard evaluation criteria .
VERY LOW
LOW
MEDIUM
HIGH
VERY HIGH
Proximity | A date to indicate the potential timing of the risk (format dd/mm/yy or mmm-yy), i.e. whether the risk is immediate or likely to occur at some point in the future. | See GUIDANCE sheet for more explanation.
If the risk is immediate then leave blank.
If the risk will occur at some future point enter the future date.
The date may change throughout the life of the risk as circumstances change. This date, along with Probability and Impact, will be used to determine the RAG Status.
Description of Risk | This must be clearly stated in terms of cause and effect along the lines of 'There is a risk of/that……………..which may result in…………….' | see Risk Management Process - Definition of Risk and Responses
Impact Description | A more comprehensive description of Impact if this is required.
Trigger | Used in conjunction with Proximity. If the risk will only manifest itself, or will grow stronger, due to some future event or circumstance then details should be recorded. | See GUIDANCE sheet for more explanation.
Original Level | The initial management level for the risk, one of: | See Risk Management Process - Guidance on Setting Risk Level & Escalation
IM BOARD (= Information Management Board level)
SUB COMMITTEE (= Strand/Programme Sub Committee Level)
PROJECT (= Project Manager or within project)
Current Level | The current management level for the risk. At creation, this should be set to the same value as Original Level. Over time it will indicate escalation or demotion of a risk when compared with Original Level. | See Risk Management Process - Guidance on Setting Risk Level & Escalation
Risk Owner | Name of individual responsible for managing the risk.
Possible Mitigating Actions | A list of possible actions that could be taken in response to the risk.
Chosen Mitigating Action | The selected action(s) to be taken. This field must be completed at Creation even if the only known action at that time is to further analyse the risk to determine possible responses.
Action Owner | Name(s) of individual(s) responsible for implementing action(s).
Action Status | A succinct description of the current progress towards completion of action(s).
Date of Last Update | Date on which the risk entry was last updated.
Action Target Date | Target date for completion of Chosen Action (format dd/mm/yy).
Issue Number | To maintain an audit trail to the Issue Register.
If the risk originated as an Issue then record the original Issue Number.
If the risk is transferred to the Issue Register then record the resulting Issue Number.
Closure Date | The date on which the risk is CLOSED or TRANSFERED (format dd/mm/yy).
Mitigation Cost | Can be used to record the cost of mitigation action.
% Likelihood | Used in conjunction with Mitigation Cost. This is the Probability of the risk expressed as a % for budgeting purposes.
Risk Budget | To hold the result of Mitigation Cost X % Likelihood to give a provision for treating the risk. If a calculation is done for all known risks on a project then the total provides a budget provision for the treatment of risk for the whole of the project.

## GUIDANCE
Guidance on Setting Probability, Impact and Proximity
Probability
Use the Criteria in the table below to assess the likelihood of a risk being realised and assign the Probability shown for that level. The three types of Criteria shown are just different ways of expressing the same level of likelihood.
| Probability | Criteria
| Very Low | Virtually impossible | < 5% likelihood | Odds > 20/1
| Low | Low but not impossible | 5% to 20% likelihood | Odds 20/1 to 5/1
| Medium | Fairly likely | 21% to 50% likelihood | Odds 5/1 to 2/1
| High | More likely than not | 51% to 80% likelihood | Odds 2/1 to 4/5
| Very High | Virtually certain | > 80% likelihood | Odds < 4/5
Impact
Impact on an activity is usually considered in terms of the effect on cost, scheduling and quality. Each of these will need to be understood in terms of its importance to the activity. Once relative importance is understood, use the Criteria in the table below to assess the effect of a risk being realised and assign the Impact shown for that level.
| Impact | Budget Criteria | Schedule Criteria | Quality Criteria
| Very Low | Negligible effect on cost, < 3% | Negligible effect on schedule, < 3% | System will fully meet mandatory requirements.
| Low | Small increase in cost, 3 to 10% | Small schedule slip, 3 to 10% | A few shortfalls in desirable functionality
| Medium | Significant increase in cost, 10 to 30% | Significant schedule slip, 10 to 30% | Minor shortfalls in one or more key requirements
| High | Large increase in cost, 30 to 75% | Large slip in schedule, 30 to 50% | Major shortfall in one or more key requirements
| Very High | Major increase in cost, > 75% | Major slip in schedule, > 50% | Major shortfall in any of the critical requirements
Proximity
Proximity reflects the timing of the risk.
If the risk is immediate then there is no need to specify Proximity. However, if a risk will only arise at some future date or as a result of some future event then a future date will be recorded.
For instance, if a parallel development or operational upgrade is intending to implement changes prior to the end of your project then there may be a risk that the changes will impact your project. However, the changes may not be implemented or may be implemented only in areas that don’t affect your project or may be piloted then rolled out when all risks are eliminated. Any potential risk to your project will only arise as the changes are implemented so the Proximity should be given the date of the intended implementation and the risk should be re-evaluated in the light of new knowledge gained as the date approaches.
Trigger
A further optional field is included in the Risk Register to be used in conjunction with Proximity. It allows for the recording of a description of any future event that generated the Proximity date and for any notes or comments that may be required.

## RAG MATRIX GRAPHIC
DEFAULT RAG (Used on ALL projects)
PROBABILITY | IMPACT | PROXIMITY
|  | < 1 month | 1 to 3 months | > 3 months
Very Low | Very Low | GREEN | GREEN | GREEN
Very Low | Low | GREEN | GREEN | GREEN
Very Low | Medium | AMBER | GREEN | GREEN
Very Low | High | AMBER | AMBER | GREEN
Very Low | Very High | RED | AMBER | AMBER
Low | Very Low | GREEN | GREEN | GREEN
Low | Low | AMBER | GREEN | GREEN
Low | Medium | AMBER | AMBER | GREEN
Low | High | RED | AMBER | AMBER
Low | Very High | RED | RED | AMBER
Medium | Very Low | AMBER | GREEN | GREEN
Medium | Low | AMBER | AMBER | GREEN
Medium | Medium | RED | AMBER | AMBER
Medium | High | RED | RED | AMBER
Medium | Very High | RED | RED | RED
High | Very Low | AMBER | AMBER | GREEN
High | Low | RED | AMBER | AMBER
High | Medium | RED | RED | AMBER
High | High | RED | RED | RED
High | Very High | RED | RED | RED
Very High | Very Low | RED | AMBER | AMBER
Very High | Low | RED | RED | AMBER
Very High | Medium | RED | RED | RED
Very High | High | RED | RED | RED
Very High | Very High | RED | RED | RED

## RAG MATRIX
HighHigh<1 | RED | VeryLow | OPEN
HighHigh>3 | RED | Low | CLOSED
HighHigh1-3 | RED | Medium | TRANSFER TO ISSUE
HighLow<1 | RED | High
HighLow>3 | AMBER | VeryHigh
HighLow1-3 | AMBER
HighMedium<1 | RED
HighMedium>3 | AMBER | Learn how to edit dropdown lists in Excel click the Mircosoft Link Below
HighMedium1-3 | RED
HighVeryHigh<1 | RED | http://office.microsoft.com/en-gb/excel-help/create-or-remove-a-drop-down-list-HP005202215.aspx
HighVeryHigh>3 | RED
HighVeryHigh1-3 | RED
HighVeryLow<1 | AMBER
HighVeryLow>3 | GREEN
HighVeryLow1-3 | AMBER
LowHigh<1 | RED
LowHigh>3 | AMBER
LowHigh1-3 | AMBER
LowLow<1 | AMBER
LowLow>3 | GREEN
LowLow1-3 | GREEN
LowMedium<1 | AMBER
LowMedium>3 | GREEN
LowMedium1-3 | AMBER
LowVeryHigh<1 | RED
LowVeryHigh>3 | AMBER
LowVeryHigh1-3 | RED
LowVeryLow<1 | GREEN
LowVeryLow>3 | GREEN
LowVeryLow1-3 | GREEN
MediumHigh<1 | RED
MediumHigh>3 | AMBER
MediumHigh1-3 | RED
MediumLow<1 | AMBER
MediumLow>3 | GREEN
MediumLow1-3 | AMBER
MediumMedium<1 | RED
MediumMedium>3 | AMBER
MediumMedium1-3 | AMBER
MediumVeryHigh<1 | RED
MediumVeryHigh>3 | RED
MediumVeryHigh1-3 | RED
MediumVeryLow<1 | AMBER
MediumVeryLow>3 | GREEN
MediumVeryLow1-3 | GREEN
VeryHighHigh<1 | RED
VeryHighHigh>3 | RED
VeryHighHigh1-3 | RED
VeryHighLow<1 | RED
VeryHighLow>3 | AMBER
VeryHighLow1-3 | RED
VeryHighMedium<1 | RED
VeryHighMedium>3 | RED
VeryHighMedium1-3 | RED
VeryHighVeryHigh<1 | RED
VeryHighVeryHigh>3 | RED
VeryHighVeryHigh1-3 | RED
VeryHighVeryLow<1 | RED
VeryHighVeryLow>3 | AMBER
VeryHighVeryLow1-3 | AMBER
VeryLowHigh<1 | AMBER
VeryLowHigh>3 | GREEN
VeryLowHigh1-3 | AMBER
VeryLowLow<1 | GREEN
VeryLowLow>3 | GREEN
VeryLowLow1-3 | GREEN
VeryLowMedium<1 | AMBER
VeryLowMedium>3 | GREEN
VeryLowMedium1-3 | GREEN
VeryLowVeryHigh<1 | RED
VeryLowVeryHigh>3 | AMBER
VeryLowVeryHigh1-3 | AMBER
VeryLowVeryLow<1 | GREEN
VeryLowVeryLow>3 | GREEN
VeryLowVeryLow1-3 | GREEN
Closed | Blue