# Stage Governance and Control
A Guide to Stage Plans, Exception Management and Stage Reporting

Author

James J. Bailey

Project Management and Business Case Advisory

Connect on LinkedIn

https://www.linkedin.com/in/jamesbailey-uk/

# Part 0. How Stage Governance Works Beneath the PID

### How to Use This Guide

This document is structured in four parts.

Part 0 explains how stage governance operates beneath the PID.

Part 1 outlines what Project Boards look for when reviewing a Stage Plan.

Part 2 provides a structured Stage Plan template.

Part 3 provides the Stage Accountability Report template.

Part 4 explains exception management and emergency stage boundaries.

You do not need to read the entire guide before drafting a Stage Plan.

Parts 0 and 1 provide context and scrutiny insight.

Parts 2 and 3 are designed for practical use.

Guidance text shown in brackets should be removed prior to submission.

## 0.1 Why Stage Control Exists

Once a project has been approved and defined in the PID, the focus shifts from justification to controlled delivery.

The PID sets out:

- Why the project is being undertaken

- What it must achieve

- How it will be governed

The Stage Plan sits directly beneath the PID. It translates strategic intent into controlled, time-bound delivery for a defined period of work.

The Project Board does not authorise daily activity.
It authorises stages.

A Stage Plan is therefore the formal contract between the Project Manager and the Project Board for that stage.

It answers one simple governance question:

“What exactly are we authorising you to deliver before you return to us?”

## 0.2 The Governance Ladder

Stage control only makes sense when understood in the context of delegated authority.

Business Authority  Project Board  Project Manager  Team Manager  Delivery Teams

In a typical governance structure, there are four levels:

- Business layer

- Project Board

- Project Manager

- Team Manager or delivery teams

Each level sets tolerances for the level below.

The Business layer sets project tolerances for the Board.
The Board sets stage tolerances for the Project Manager.
The Project Manager sets work package tolerances for delivery teams.

Tolerances typically apply to:

- Time

- Cost

- Scope

- Quality

- Risk

- Benefits

As long as performance is forecast to remain within agreed tolerances, authority remains delegated.

If tolerances are forecast to be exceeded, authority moves upward.

This is the foundation of controlled management by exception.

## 0.3 The Stage Boundary Logic

Projects are not authorised in one single block of uncontrolled work.

They are broken into stages for three reasons:

- To improve forecasting accuracy

- To allow periodic governance review

- To manage risk progressively

At the end of each stage:

- The Project Manager reports performance

- The Business Case is reviewed

- The next Stage Plan is presented

- The Board decides whether to authorise continuation

This creates a deliberate pause in authority.

The Board does not simply receive information.
It makes an active decision.

## 0.4 What Happens When Tolerances Are Forecast to Be Breached

If at any point during a stage the Project Manager forecasts that stage tolerances will be exceeded, the situation becomes an exception.

An exception does not mean failure.
It means delegated authority has been exhausted.

When this occurs:

- The Project Manager escalates the issue to the Project Board.

- An Exception Report outlines the situation and possible options.

- The Board decides how to proceed.

If recovery requires a fundamental replan of the stage, an Exception Plan is produced.

An Exception Plan replaces the current Stage Plan.

Although the project may be mid-stage, this effectively creates an emergency stage boundary. The Board must review and re-authorise a revised plan before work proceeds under new parameters.

This mechanism protects governance integrity.

## 0.5 The Control Loop

Across the life of a project, the control rhythm becomes:

- Authorise Stage

- Deliver Stage

- Report Performance

- Review Business Case

- Authorise Next Stage

Or, if tolerances are forecast to be exceeded:

- Escalate

- Replan

- Re-authorise

The Stage Plan and the End Stage Report are the two formal documents that make this control loop visible and defensible.

They are not administrative paperwork.

They are governance instruments.

# Part 1. What Reviewers Actually Look For in a Stage Plan

A Stage Plan is not reviewed for formatting quality.
It is reviewed for control credibility.

When a Project Board reviews a Stage Plan, they are asking one question:

“Are we comfortable delegating authority for this stage?”

Everything else is secondary.

Below are the areas experienced reviewers focus on, whether they articulate them explicitly or not.

## 1.1 Clarity of Stage Objectives

The Board first checks whether the purpose of the stage is clear.

Example: Produce an approved technical design pack enabling procurement of the build contractor.

They want to understand:

- What this stage is meant to achieve

- How it contributes to overall project objectives

- Whether the scope is proportionate and realistic

If the objectives are vague, over-ambitious or disconnected from the Business Case, confidence drops immediately.

A strong Stage Plan clearly states:

- The outcomes expected at the end of the stage

- The measurable criteria for completion

- The linkage back to the approved PID

If the stage ends, what will exist that does not exist today?

That must be obvious.

## 1.2 Defined Deliverables, Not Just Activities

Experienced reviewers do not look for task lists.

They look for products.

They want to see:

- What tangible outputs will be delivered

- Who owns each deliverable

- How acceptance will be confirmed

A Stage Plan that focuses only on activities creates ambiguity.

A Stage Plan that defines products, milestones and acceptance criteria demonstrates control.

The question in a reviewer’s mind is:

“If we authorise this stage, what exactly will we receive?”

## 1.3 Credible Schedule and Milestones

Boards understand that plans evolve.

They are not looking for perfection.

They are looking for realism.

They will check:

- Are milestone dates clearly defined?

- Are critical dependencies visible?

- Is the duration proportionate to the scope?

- Is there evidence of proper planning rather than guesswork?

A strong Stage Plan does not attempt to look optimistic.

It demonstrates that time has been thought through.

Clear milestone reporting points are particularly important, as they allow the Board to understand when they will next receive structured visibility.

1.4 Cost and Resource Transparency

Reviewers will look closely at the cost profile.

They want to know:

- What budget is required for this stage

- How that compares to the overall project envelope

- Where major cost drivers sit

- Whether resource assumptions are explicit

A Stage Plan should show:

- Forecast spend for the stage

- Key resource roles or categories

- Any material procurement or contractual exposure

If costs appear disconnected from the scope, confidence reduces.

The Board is delegating financial authority for that stage. That must feel proportionate and justified.

## 1.5 Risk Profile and Exposure

No stage is risk-free.

Boards expect risk.

What they look for is risk awareness.

A strong Stage Plan demonstrates:

- The key risks affecting this stage

- The mitigation strategy

- Who owns each risk

- Whether any risk threatens stage tolerances

If the risk section is empty or generic, it signals superficial planning.

If it is realistic and prioritised, it signals maturity.

Reviewers are not looking for exhaustive risk registers.
They are looking for insight.

## 1.6 Tolerances and Delegated Authority

This is one of the most important sections.

Boards want clarity on:

- What tolerances they are setting for time, cost, scope, quality, risk and benefits

- What level of deviation is acceptable without further escalation

- What would trigger an exception

If tolerances are unclear, authority is unclear.

A well-defined tolerance statement reassures the Board that:

- Control exists

- Escalation thresholds are understood

- Governance will not be bypassed

This is where management by exception becomes visible in practice.

## 1.7 Control and Reporting Arrangements

The Board wants to know how they will stay informed.

They look for clarity on:

- Reporting frequency

- Highlight report timing

- Key review points

- Any formal assurance activity

A Stage Plan should explain how performance will be monitored and reported.

This demonstrates that control is active, not reactive.

## 1.8 Alignment with the Business Case

Even though the detailed economic justification sits in the Business Case, reviewers will still consider:

- Does this stage protect the agreed benefits?

- Does it remain aligned to the original justification?

- Is there any emerging impact on value for money?

A strong Stage Plan briefly confirms that alignment remains intact.

It reassures the Board that delivery and justification are still connected.

If a stage materially alters cost, timing or scope without reviewing the Business Case, governance discipline has broken down.

## 1.9 The Silent Question Behind Every Review

Behind all the headings and tables, there is a silent test:

“Does this Project Manager appear in control?”

A Stage Plan that is:

- Clear

- Structured

- Proportionate

- Realistic

- Explicit about risk and tolerances

Builds trust.

A Stage Plan that feels rushed, vague or overly optimistic weakens delegated authority.

The purpose of this guide is not simply to help you complete a template.

It is to help you present a Stage Plan that a Board can authorise with confidence.

# Part 2. The Stage Plan Template

(The High Authority Stage Plan Template)

This template is designed to help you produce a Stage Plan that can withstand real governance scrutiny.

Guidance is shown in brackets and should be removed in the final document.

The structure is intentionally clear and proportionate. It is suitable for both public and private sector governance environments.

## 2.1 Document Control

### Stage Plan

Project Title:
Stage Name / Number:

Version:
Date:

Author:
Approved by:

Stage Authorisation Date:
Stage Start Date:
Planned Stage End Date:

Document Classification: Official / Confidential / Commercial in Confidence

(Ensure this page makes it clear that this is the version being submitted for Board authorisation. Clarity of version control builds credibility.)

## 2.2 Executive Summary

(Provide a concise summary of the stage. This should not exceed one page.)

The Executive Summary should cover:

- The purpose of this stage

- What will be delivered

- The duration

- The total forecast cost

- Key risks

- The tolerances being requested

- The recommendation for authorisation

Example structure:

This Stage Plan sets out the work required to deliver [summary of key outcomes]. The stage will run from [date] to [date] and requires a budget of £[amount]. Key risks include [summary]. Stage tolerances are proposed as [summary]. Approval of this plan will authorise delivery of the defined scope under delegated authority.

(This section is often the only part read in detail before discussion. Make it disciplined and confident.)

## 2.3 Stage Objectives

(Clearly define what this stage is intended to achieve.)

Include:

- The purpose of the stage

- The outcomes expected at completion

- How the stage supports the overall project objectives

- Any measurable success criteria

Prompt questions:

- What will exist at the end of this stage that does not exist today?

- What decision or progression does this stage enable?

- How will we know the stage is complete?

Avoid vague statements. Focus on tangible outcomes.

## 2.4 Deliverables and Product Descriptions

(Define what will be delivered during this stage.)

Include a table such as:

| Deliverable | Description | Owner | Acceptance Criteria | Planned Completion |
| --- | --- | --- | --- | --- |

Guidance:

- Focus on products, not activities.

- Ensure each deliverable has a named owner.

- Define how acceptance will be confirmed.

(Boards authorise outputs. Make them visible.)

## 2.5 Delivery Approach

(Describe how the work will be delivered.)

Include:

- Delivery model (in-house, outsourced, hybrid)

- Key workstreams

- Dependencies between major elements

- Any procurement or contractual steps

- Governance interfaces

Prompt questions:

- Is this stage exploratory, build-focused, or transition-focused?

- What sequencing logic underpins the schedule?

- Are there any critical external approvals?

This section demonstrates thoughtfulness rather than optimism.

## 2.6 Schedule and Major Milestones

(Provide a clear view of timing.)

Include:

- Stage start and end date

- Key milestone dates

- Board review points

- Assurance checkpoints

A milestone table is often sufficient:

| Milestone | Planned Date | Description | Owner |
| --- | --- | --- | --- |

If a Gantt chart is used, ensure it supports rather than replaces narrative clarity.

Prompt questions:

- What events must occur for the stage to remain on track?

- When will the Board next receive formal reporting?

## 2.7 Resource and Cost Profile

(Show how the stage will be resourced and funded.)

Include:

- Summary of resource roles or categories

- Stage budget

- Forecast monthly or milestone-based spend

- Key cost drivers

Example cost summary table:

| Cost Category | Forecast Cost (£) |
| --- | --- |
| Internal Resource |  |
| External Suppliers |  |
| Contingency |  |
| Total |  |

Prompt questions:

- Are assumptions about availability explicit?

- Is contingency proportionate to risk exposure?

Transparency builds trust.

## 2.8 Risk Profile

(Highlight the most significant risks affecting this stage.)

Include:

| Risk ID | Description | Impact | Likelihood | Owner | Mitigation |
| --- | --- | --- | --- | --- | --- |

Guidance:

- Focus on material risks.

- Avoid generic statements.

- Identify risks that could threaten tolerances.

Prompt questions:

- Which risks could trigger escalation?

- Are mitigation actions realistic and funded?

Boards expect risk awareness, not risk elimination.

## 2.9 Dependencies and Assumptions

(Capture critical factors outside direct control.)

Dependencies may include:

- External approvals

- Supplier commitments

- Regulatory input

- Inter-project interfaces

Assumptions should be explicit and realistic.

Prompt question:

- If this assumption proves false, what would change?

This section demonstrates maturity of planning.

## 2.10 Stage Tolerances

(Clearly define the delegated authority boundaries.)

Specify tolerances for:

- Time

- Cost

- Scope

- Quality

- Risk

- Benefits (if applicable)

Example format:

- Time: +/- X weeks

- Cost: +/- £X

- Scope: Defined in section 2.4

- Risk: Exposure must not exceed agreed threshold

Guidance:

Be explicit. Avoid vague language such as “within reasonable limits”.

This section defines when escalation becomes mandatory.

## 2.11 Control and Reporting Arrangements

(Explain how the stage will be monitored.)

Include:

- Highlight reporting frequency

- Risk and issue review cycle

- Assurance activities

- Change control process

- Stage boundary timing

Prompt questions:

- How will performance against plan be tracked?

- When will the Business Case be reviewed?

- What triggers an Exception Report?

This section demonstrates active control rather than passive reporting.

## 2.12 Recommendation

Conclude with a clear statement:

The Project Manager recommends that the Project Board authorise delivery of this stage in accordance with the defined scope, budget, schedule and tolerances.

Avoid ambiguity.

A Stage Plan is submitted for decision.

# Part 3. The Stage Accountability Report

(End Stage Report / End Project Report Template)

The Stage Accountability Report is the formal record of how the authorised Stage Plan performed.

It is not a narrative update.
It is a governance document.

Its purpose is to enable the Project Board to decide whether:

- The stage has been completed satisfactorily

- The Business Case remains viable

- The next stage should be authorised

- Corrective action is required

The same structure can be used for an End Project Report, with the emphasis shifting to overall performance against the PID.

Guidance is shown in brackets and should be removed in the final document.

## 3.1 Document Control

### Stage Accountability Report

Project Title:
Stage Name / Number:

Version:
Date:

Author:
Submitted to:

Stage Start Date:
Stage End Date:
Stage Authorised Budget

Document Classification: Official / Confidential / Commercial in Confidence

(Ensure clarity on which Stage Plan this report is assessing.)

## 3.2 Executive Summary

(Provide a concise summary of stage performance.)

This section should allow the Board to understand, within one page:

- Whether the stage objectives were achieved

- Whether delivery remained within tolerance

- The overall cost and schedule performance

- The current risk position

- Any impact on the Business Case

- The recommendation

Example structure:

This report summarises performance for Stage [number]. The stage delivered [summary of key outputs]. The stage completed on [date], within the authorised tolerances for time and cost. Key risks remaining relate to [summary]. There has been / has not been any material change to the Business Case. It is recommended that [next stage be authorised / corrective action be taken / project be closed].

This section should be factual and balanced.

## 3.3 Stage Performance Against Objectives

(Assess whether the objectives defined in the Stage Plan were achieved.)

Include:

- Original stage objectives

- Actual outcomes

- Variances

- Explanation for material deviation

Prompt questions:

- Were the defined outcomes achieved?

- Were acceptance criteria met?

- Were any objectives deferred or descoped?

Avoid defensive language. Provide clear explanation.

## 3.4 Product Status

(Summarise deliverables planned versus delivered.)

Include a table such as:

| Deliverable | Planned Completion | Actual Completion | Status | Commentary |
| --- | --- | --- | --- | --- |

Guidance:

- Clearly identify completed, partially completed, or deferred products.

- If deliverables were not achieved, explain impact and recovery approach.

Boards focus on outputs, not activity levels.

## 3.5 Time and Schedule Performance

(Report performance against the authorised schedule.)

Include:

- Planned stage end date

- Actual stage end date

- Variance

- Cause of variance

- Impact on overall project timeline

Prompt questions:

- Were any milestones missed?

- Did any delay threaten tolerances?

- Were any corrective actions required?

Transparency builds credibility.

## 3.6 Cost Performance

(Report actual spend against authorised budget.)

Include a summary table:

| Cost Category | Budget (£) | Actual (£) | Variance (£) | Commentary |
| --- | --- | --- | --- | --- |

Guidance:

- Identify material variance

- Explain drivers of overspend or underspend

- Confirm whether tolerance thresholds were breached

If contingency was used, explain how and why.

## 3.7 Risk and Issue Overview

(Summarise risk exposure during the stage.)

Include:

- Number of risks at start of stage

- Number closed

- Number escalated

- Number remaining open

- High exposure risks moving into next stage

Include a short narrative:

The key risk themes during this stage were [summary]. The current risk profile for the project is [low / moderate / elevated], primarily driven by [key drivers].

Boards are interested in trend and exposure, not full registers.

## 3.8 Quality and Assurance Summary

(Confirm that quality controls were applied as planned.)

Include:

- Summary of reviews conducted

- Any significant defects

- Any rework required

- Lessons regarding quality controls

Prompt questions:

- Were acceptance processes followed?

- Did any quality failure threaten stage objectives?

This confirms control discipline.

## 3.9 Business Case Review

(This is critical.)

Confirm:

- Whether the Business Case remains valid

- Whether forecast benefits remain achievable

- Whether cost changes affect value for money

- Whether strategic alignment remains intact

If there has been material change, state clearly.

This section links delivery back to justification.

Without this, governance is incomplete.

## 3.10 Lessons and Key Experiences

(Capture structured learning.)

Include:

- Key events affecting stage performance

- What worked well

- What did not work as expected

- Implications for future stages

Lessons should be concise and practical.

Avoid generic statements.

## 3.11 Recommendation to the Project Board

Conclude with a clear decision request.

Examples:

It is recommended that the Project Board:

- Confirm satisfactory completion of Stage [number]

- Authorise Stage [number + 1] in accordance with the submitted Stage Plan

Or, where appropriate:

- Approve corrective action

- Approve an Exception Plan

- Close the project

A Stage Accountability Report always leads to a decision.

# Part 4. Exception Plans and Emergency Stage Boundaries

Most governance failures do not occur during normal delivery.
They occur when control thresholds are crossed and authority becomes unclear.

Exception management exists to prevent that.

This section explains:

- What constitutes an exception

- How tolerances trigger escalation

- When an Exception Plan is required

- Why an Exception Plan effectively creates an emergency stage boundary

## 4.1 What Is an Exception?

An exception occurs when the Project Manager forecasts that stage tolerances will be exceeded.

This is important.

An exception is triggered by forecast, not by hindsight.

If time, cost, scope, quality, risk or benefit tolerances are forecast to be breached, delegated authority has been exhausted.

The Project Manager may not continue delivery under the existing Stage Plan without escalation.

This is not failure.

It is the governance mechanism functioning correctly.

## 4.2 The Role of Tolerances

Tolerances define the limits of delegated authority.

Within agreed tolerances, the Project Manager may manage delivery without seeking further approval.

Once tolerances are forecast to be exceeded:

- Authority reverts upward

- The Project Board must decide how to proceed

Typical tolerance categories include:

- Time

- Cost

- Scope

- Quality

- Risk

- Benefits

A clear Stage Plan defines tolerances explicitly.

If tolerances are vague, exception handling becomes subjective.

Clarity protects both the Project Manager and the Board.

## 4.3 The Exception Process

When an exception is forecast:

- The Project Manager prepares an Exception Report.

- The Project Board reviews the impact.

- The Board decides whether to:

  - Approve corrective action within revised limits

  - Request an Exception Plan

  - Terminate the stage or project

The Exception Report should summarise:

- What tolerance is forecast to be breached

- Why

- The impact on time, cost, scope and risk

- Options available

- A recommended course of action

This ensures the Board remains informed before loss of control occurs.

## 4.4 What Is an Exception Plan?

An Exception Plan replaces the current Stage Plan.

It is not an addendum.

It is a revised, fully costed and scheduled plan for the remainder of the stage.

Although the project may be mid-stage, the approval of an Exception Plan creates what is effectively an emergency stage boundary.

The Board must:

- Review revised forecasts

- Confirm that the Business Case remains viable

- Set new tolerances

- Re-authorise delivery

This resets delegated authority under revised conditions.

## 4.5 When Is an Exception Plan Required?

An Exception Plan is typically required when:

- Recovery action requires re-scoping the stage

- Budget must increase beyond agreed tolerance

- The schedule must extend beyond tolerance

- Risk exposure materially changes

- External events invalidate original assumptions

- Minor corrective action within tolerance does not require an Exception Plan.

Only forecast breach of tolerance triggers formal escalation.

This distinction is critical.

## 4.6 Content of an Exception Plan

An Exception Plan mirrors the structure of a Stage Plan.

It should include:

- Revised stage objectives

- Updated deliverables

- Updated schedule and milestones

- Revised cost profile

- Updated risk assessment

- Revised tolerances

- Impact on overall project timeline

- Confirmation of Business Case viability

It must clearly state:

- What has changed

- Why

- What the revised forecast is

- What approval is being requested

Transparency is essential.

## 4.7 Governance Discipline in Practice

Exception management is often misunderstood.

Some Project Managers avoid escalation in order to “solve it quietly.”

This weakens governance.

Some Boards overreact to exceptions, viewing them as failure.

This discourages honest forecasting.

Proper exception handling should feel procedural, not political.

It demonstrates:

- Forecasting discipline

- Accountability

- Respect for delegated authority

- Protection of the Business Case

A mature governance environment treats exceptions as control events, not reputational crises.

## 4.8 The Control Principle

The control loop across a stage becomes:

- Plan

- Authorise

- Deliver

- Monitor

- Forecast

- Escalate if required

- Re-authorise

The Stage Plan defines delegated authority.
The End Stage Report proves performance.
The Exception Plan protects governance integrity when conditions change.

Together, they ensure that no project continues under unexamined assumptions.

# Annex A. Using AI Responsibly When Drafting Stage Plans and Stage Reports

Artificial intelligence tools can assist with structuring and drafting Stage Plans, Stage Accountability Reports and Exception Plans.

They do not replace governance judgement, forecasting discipline or Board accountability.

Stage documentation is not an academic exercise. It is a delegation instrument.
Responsibility for its accuracy and integrity always remains with the Project Manager.

## A.1 Appropriate Use of AI in Stage Planning

AI tools can support:

- Structuring Stage Plan sections

- Refining written clarity

- Summarising workshop outputs

- Drafting milestone descriptions

- Reformatting risk summaries

- Improving narrative coherence

AI is particularly useful when:

- Turning notes into structured sections

- Converting meeting outputs into formal wording

- Stress testing clarity of objectives

- Reviewing tone for governance appropriateness

AI should not be used to:

- Invent cost assumptions

- Fabricate delivery milestones

- Create risks that have not been identified

- Estimate budgets without real data

- Generate artificial confidence

Stage Plans must reflect actual delivery capability and constraints.

## A.2 Structured AI Workflow for Stage Plans

When using AI to support drafting, apply a disciplined approach.

### Step 1 – Define the Role

Example:

“You are an experienced Project Board reviewer assessing a Stage Plan for governance credibility.”

This improves relevance of feedback.

Step 2 – Provide Context

Include:

- Project scale

- Stage objectives

- Budget range

- Delivery model

- Known constraints

- Tolerance thresholds

Without context, AI output becomes generic.

### Step 3 – Specify the Task

Examples:

“Draft a clear Executive Summary for a Stage Plan seeking Board authorisation.”
“Review the following risk section and identify areas that appear weak.”
“Rewrite this tolerance section to make escalation triggers explicit.”

Be precise.

### Step 4 – Provide Source Material

Paste:

- Workshop notes

- Milestone tables

- Risk summaries

- Budget assumptions

Avoid asking AI to generate substantive content from nothing.

AI should refine evidence, not replace it.

### Step 5 – Review and Validate

Always:

- Check factual accuracy

- Confirm numbers match financial models

- Confirm milestone dates align with schedules

- Confirm tolerance thresholds match Board approval

The Project Manager remains accountable.

## A.3 Using AI for Stage Accountability Reports

AI can assist in:

- Summarising performance data

- Drafting neutral variance explanations

- Clarifying recommendation wording

- Improving readability

However:

- Performance data must be real

- Variance explanations must be accurate

- Risk exposure must reflect current registers

Boards quickly identify generic or overly polished language that does not match reality.

Use AI to improve clarity, not to conceal performance issues.

## A.4 Using AI in Exception Scenarios

Exception management requires particular care.

AI may assist in:

- Structuring an Exception Report

- Comparing original and revised tolerances

- Clarifying impact statements

It must not:

- Minimise forecast breaches

- Reframe material variance as minor

- Remove explicit statements of tolerance breach

Exception documentation must remain transparent.

## A.5 Professional Responsibility

AI can assist with structure and language.

It cannot:

- Replace delivery judgement

- Replace stakeholder engagement

- Replace financial modelling

- Replace risk ownership

- Defend the plan in front of a Project Board

Only disciplined preparation can do that.

AI is a drafting assistant.
It is not a governance substitute.